## Gantt
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
WP0 – Project management
T0.1 – Project control
T0.2 – Quality and documentation management
T0.3 – Administrative and financial management
WP1 - Analysis of mobility services and impact of project results on society and business
T1.1 – Stakeholder and user groups identification
T1.2 – User mobility patterns and needs
T1.3 – OMNIBUS infrastructure and services
T1.5 – User profiles and trade-off analysis
WP2 – Context acquisition and analysis
T2.1 – Context acquisition module
T2.2 – Data preparation and context-aware filtering
T2.3 – Data mining within content associated to user context
T2.4 - Knowledge representation
WP3 – Mobility ICT infrastructure
T3.1 Numerical models to predict the traffic flow dynamics
T3.2 Optimization models and algorithms for (dynamic) dial-a-ride type of problems
T3.3 Mobility service composition design
T3.4 Communication Network Infrastructure
WP4 – Service marketplace
T4.1 Mobility Service Marketplace
T4.2 Support to communities of users
T4.3 Support to mobility service execution
T4.4 Informational services supporting mobility
WP5 – Integration
T5.1 – OMNIBUS system architecture
T5.2 – Model-based infrastructure to support WPs interoperability
T5.3 – Integration management of technical solutions
WP6 – Pilot cases
T6.1 – Elicitation and abstraction of pilot site requirements
T6.2 – Deployment and evaluation of Larisa pilot
T6.3 – Deployment and evaluation of L'Aquila pilot

## Effort
| A | B | C | D | E | F | G | H | Total
WP0 Project management | 15 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 17
Task 0.1 Project control | A: 5; B: 0.75; Total: 5.75
Task 0.2 Quality and documentation management | A: 5; B: 0.5; Total: 5.5
Task 0.3 Administrative and financial management | A: 5; B: 0.75; Total: 5.75
WP1 Analysis of mobility services and impact of project results on society and business | 1.5 | 3 | 8 | 0 | 9.5 | 10 | 3 | 6.5 | 41.5
Task 1.1 Stakeholder and user groups identification |  |  | 1 |  | 3.5 | 3 | 2 | 2.5 | 12
Task 1.2 User mobility patterns and needs |  | 1.5 | 1 |  | 3.5 | 2 |  | 2 | 10
Task 1.3 OMNIBUS infrastructure and services | A: 1.5; C: 2; F: 2; H: 1; Total: 6.5
Task 1.4 User profiles and trade-off analysis |  | 1.5 | 4 |  | 2.5 | 3 | 1 | 1 | 13
WP2 Context acquisition and analysis | 0 | 3 | 0 | 18 | 22.5 | 3 | 0 | 1.5 | 48
Task 2.1 Context acquisition module | D: 18; E: 8; F: 1; Total: 27
Task 2.2 Data preparation and context-aware filtering | E: 4; F: 2; Total: 6
Task 2.3 Data Mining within content associated to user context | E: 7; H: 1.5; Total: 8.5
Task 2.4 Knowledge representation | B: 3; E: 3.5; Total: 6.5
WP3 Mobility ICT infrastructure | 0 | 6 | 39 | 0 | 5 | 8 | 0 | 1 | 59
Task 3.1 Numerical models to predict the traffic flow dynamics | C: 15; E: 2; F: 2; Total: 19
Task 3.2 Optimization models and algorithms for (dynamic) dial-a-ride type of problems | C: 15; E: 2; H: 1; Total: 18
Task 3.3 Mobility service composition design | B: 6; C: 9; E: 1; F: 2; Total: 18
Task 3.4 Communication Network Infrastructure | F: 4; Total: 4
WP4 service marketplace | 4 | 30 | 2 | 15 | 2 | 8 | 0 | 0 | 61
Task 4.1 Mobility Service Marketplace | A: 2; B: 8; D: 7.5; F: 2; Total: 19.5
Task 4.2 Support to communities of users | 2 | 8 |  | 7.5 | 2 | 2 |  |  | 21.5
Task 4.3 Support to mobility service execution | B: 8; C: 2; F: 2; Total: 12
Task 4.4 Informational services supporting mobility | B: 6; F: 2; Total: 8
WP5 Integration | 21 | 5 | 14 | 0 | 6 | 10 | 0 | 0 | 56
Task 5.1 OMNIBUS system architecture | 3 | 4 | 4 |  | 4 | 4 |  |  | 19
Task 5.2 Model-based infrastructure to support WPs interoperability | A: 2; C: 8; F: 2; Total: 12
Task 5.3 Integration management of technical solutions | 16 | 1 | 2 |  | 2 | 4 |  |  | 25
WP6 Pilot Cases | 16 | 3 | 2 | 0 | 4.5 | 8 | 7 | 8.5 | 49
Task 6.1 Elicitation and abstraction of pilot site requirements | E: 2; F: 2; G: 1; H: 2.5; Total: 7.5
Task 6.2 Deployment and evaluation of Larisa pilot | 8 | 1.5 |  |  | 2.5 | 3 |  | 6 | 21
Task 6.3 Deployment and evaluation of L'Aquila pilot | 8 | 1.5 | 2 |  |  | 3 | 6 |  | 20.5
TOTAL (ALL ACTIVITIES) | 57.5 | 52 | 65 | 33 | 49.5 | 47 | 10 | 17.5 | 331.5